## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Moon Game |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-08-29
Michael Perry (GL), Robert Knapp, Joshua Caufaglione, Brandon Koszyk, Jeiss Varghese, Luis Rendon, Benjamin Jon
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 | W2 9/12/2022 |  | W3 9/19/2022 | W4 9/26/2022 | W5 10/3/2022 | W6 10/10/2022 | W7 10/17/2022 | W8 10/24/2022 | W9 10/31/2022 | W10 11/7/2022 | W11 11/14/2022 | W12 11/21/2022 | W13 12/28/2022 | W14 12/5/2022
1 | Setup
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-05 | 0 | 100%
1.3 | Assigning Group Leader | All | 2022-09-05 | 2022-09-05 | 0 | 100%
2 | Project Conception and Initiation
2.1 | Landscape | JC |  |  | 0
2.2 | Physics, picking up items | RK, BK |  |  | 0
2.3 | Sounds |  |  |  | 0
2.3.1 | Lighting |  |  |  | 0
2.4 | Menus and UI |  |  |  | 0
2.5 | Map/Level Layout |  |  |  | 0
2.6 | Narrative/Story | JC |  |  | 0
2.7 | Watch function |  |  |  | 0
2.8 |  |  |  |  | 0
2.9 |  |  |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
3 | Design
3.1 | Rubiks Cube Puzzle | RK |  |  | 0
3.2 | Player Model | RK |  |  | 0
3.2.1 | Inventory | BJ |  |  | 0
3.2.2 | Gun | BK |  |  | 0
3.3 | Oxygen System | LB |  |  | 0
3.3.1 | Keypad/door mechanism | MP |  |  | 0
| Observatory and stars |  |  |  | 0
| Radio tuning |  |  |  | 0
| Computer |  |  |  | 0
0
0
0
0
4 | Parts and Assembly
4.1 |  |  |  |  | 0
4.2 |  |  |  |  | 0
4.2.1 |  |  |  |  | 0
4.2.2 |  |  |  |  | 0
4.3 |  |  |  |  | 0
4.3.1 |  |  |  |  | 0