## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Moon Game |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-08-29
Michael Perry (GL), Robert Knapp, Joshua Caufaglione, Brandon Koszyk, Jeiss Varghese, Luis Rendon, Benjamin Jon
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 9/5/2022 | W2 9/12/2022 |  | W3 9/19/2022 |  |  |  |  | W4 9/26/2022 |  |  |  |  | W5 10/3/2022 |  |  |  |  | W6 10/10/2022 |  |  |  |  | W7 10/17/2022 |  |  |  |  | W8 10/24/2022 |  |  |  |  | W9 10/31/2022 |  |  | W10 11/7/2022 |  |  |  |  | W11 11/14/2022 |  |  | W12 11/21/2022 |  |  |  |  | W13 12/28/2022 |  |  |  | W14 12/5/2022
1 | Setup
1.1 | Setting up Github | All | 2022-09-05 | 2022-09-05 | 0 | 100
1.1.1 | Setting up Webex Account | All | 2022-09-05 | 2022-09-05 | 0 | 100
1.2 | Setting up XAMPP / Unreal Engine | All | 2022-09-05 | 2022-09-05 | 0 | 100
1.3 | Assigning Group Leader | All | 2022-09-05 | 2022-09-05 | 0 | 100
2 | Project Conception and Initiation
2.1 | Landscape | JC | 2022-10-17 |  | 0 | 75 | [23 empty] | X | X | X | X | X
2.3 | Sounds | JC | 2022-09-26 |  | -44186 | 50 | [8 empty] | X | X | X | X | X | X | X | X
2.3.1 | Lighting | JC | 2022-10-06 |  | 0 | 25 | [16 empty] | X | X | X | X | X | X | X
2.5 | Map/Level Layout | JC | 2022-09-19 |  | -44179 | 25 |  |  |  | X | X | X | X | X
2.6 | Narrative/Story | JC |  |  | 0
2.2 | Physics, picking up items | RK, BK |  |  | 0
2.7 | Watch function |  |  |  | 0
2.8 |  |  |  |  | 0
2.9 |  |  |  |  | 0
2.4 | Menus and UI | LR |  |  | 0
2.1 |  |  |  |  | 0
2.11 |  |  |  |  | 0
3 | Design
3.1 | Rubiks Cube Puzzle | RK |  |  | 0
3.2 | Player Model | RK |  |  | 0
3.2.1 | Lock/Unlock Door with Key | BJ | 2022-10-03 |  | 3 | 100 | [13 empty] | X |  |  | X | X
3.2.2 | Inventory | BJ | 2022-10-16 |  | 15 | 90 | [20 empty] | X | X | X |  |  |  | X | X |  | X | X |  |  |  |  | X |  |  |  | X | X | [10 empty] | X | X | X | X | X
3.3 | Trash Bins | BJ | 2022-11-07 |  |  | 80 | [36 empty] | X
3.3.1 | Snake Game | BJ | 2022-11-08 |  | 10 | 95 | [38 empty] | X |  | X |  | X | X |  | X |  | X |  | X | X | X | X
| Observatory and stars | BJ | 2022-10-20 |  | 9 | 90 | [26 empty] | X |  |  | X | X |  |  |  |  | X | X | X | [9 empty] | X | X | X
| Computer Code Puzzle | BJ | 2022-11-18 |  | 5 | 100 | [43 empty] | X |  |  | X | X | X | X
| Light puzzle | BK |  |  | 0 | 100
| Moving Light puzzle | BK |  |  | 0 | 100
| Gun | BK |  |  | 0 | 100
| Computer | MP | 2022-10-22 |  | 0 | 75 | [26 empty] | X |  |  | X | X |  |  |  | X | X | X |  |  | X | X | X |  | X | X |  |  |  | X
| Keypad/door mechanism | MP |  |  | 0 | 100 | [15 empty] | X |  | X | X |  | X | X | X |  |  |  | X |  |  |  | X | X | X |  | X |  | X |  |  | X
| Oxygen System | LB |  |  | 0
| Radio tuning | JV | 2022-10-25 |  | 0 | 5
4 | Parts and Assembly
4.1 | Sliding Doors | JC | 2022-09-19 | 2022-09-21 | 2 | 100 |  |  |  | X | X
4.2 |  |  |  |  | 0
4.2.1 |  |  |  |  | 0
4.2.2 |  |  |  |  | 0
4.3 |  |  |  |  | 0
4.3.1 |  |  |  |  | 0